## Лист1
SUSTAINABILITY PLAN Period concerned: 15th October 2019 – 14th October 2024
Deliverables | Result | Goal | Activities | Target users | Champions | Financial resources and costs | Indicators
| What? | Why? | How? | Whom for/at? | Who is in charge? | How much? | How to track progress and measure success?
| Which are the outputs and outcomes to sustain after the project end? | Why is a certain outcome/output important and what is the goal of sustaining it? | What are the activities planned to ensure each result’s sustainability | Who are the target users and beneficiaries? | Who are persons in charge/champions? | What are the expected costs and what financial resources will be used? | What are the relevant indicators to measure progress and success?
D1.1 & D1.5 | 1. Data Collection tool on IoHE 2. IoHE online benchmarking tool | To support development of the internationalization of education, research and services of higher education in Moldova at institutional and system levels. | 1. Annual data collection "Survey on IoHe in Moldova"; 2. Annual updating of the online benchamrking tool; 3. Extention of the online benchmarking tool (includinh Eastern partnership and Mediterranian countries); 4. Maintainence and technical updating of the online benchamrking tool | Students and personnel of HEIs, stackeholders (Ministry of Education, think-tank, etc) | 1. Rectors 2. Vice-rector for international affairs 3. Head of International Relations Offices/Departments | 1. space maintenance and service costs 2. protocol expenses 3. office supplies / consumables The expenses will be covered from institutional sources, sources accumulated from sponsors. | 1. number of reports/ survey collected 2. number of rankings joined and places obtained
D2.1 | Improved skills of members of the National Policy Task Force Group in Moldova | Mainstriming of policy development in the field of Internationalisation of Higher Education in Moldova; | 1. To present the results of the ELEVATe project at the National Rectors` Council meeting; 2) to transfer NPTFG role and tasks within the ELEVATe project to the continuouse support by the members of the National Rectors` Council; 3) Advocating and policy development/ by laws on IoHE, research and services at national level. | HEIs` academic and administrative staff, researchers, National Rectors` Council, Ministry of Education | 1. National Rectors` Council members | 1. space maintenance and service costs 2. protocol expenses 3. office supplies / consumables The expenses will be covered from institutional sources, sources accumulated from sponsors. | 1. number of by laws proposed and adopted; 2) number of initiatives proposed to the Ministry of Education (brochure/ or platform "Study in Moldova", 3) number of inter-ministerial agreements on organisation of Moldovan Educational Fairs abroad (ex. Central Asia countries, Turkey, Ukraine, Azerbaijan, etc)
D2.3-D2.6 | 1. Recommendations-framework for the initiation and organisation of joint and double higher education study programmes; 2) Recommendations-framework on organisation of academic mobility and recognition of the mobility periods; 3) National Roadmap on IoHE in Moldova; 4) national information service (data collection tool) on IoHE. | 1. To strengthen quality of teaching and learning environment through stimulation of higher education institutions from Moldova in organisation of double and joint degree study programmes; 2. To improve quality of implementation procedures for mobilities and recognition of qualifications for students and staff (academic/administrative) on national level; 3. To improve the existing legislative framework, outlinening the orientation on internationalisation strategic goals and indicators and stimulating the HEIs of Moldova to pay special attention to main EHEA principles. 4. To identify missing criteria for assessing of internationalisation of higher education inside and outside the borders; 5. To stimulate the Molddovan HEIs to provide qualitative data on internationalisation, serving a reference and stimulation for growth within the country. | 1. To organise the national workshops for HEIs of Moldova dedicated to internationalisation; 2. To ensure communication between HEIs within the country and with the Ministry of Education Culture and Research of the Republic of Moldova by providing contant support and feedback on implementation of internationalisation legislative framework; 3. To inform academic community throuh online information sessions or other virtual channels on opportunities and advantges of nationaal benchmarking tool; 4. To update the inforamtion annualy by stimulating the HEIs of Moldova in providing the qualitative data in times. | Ministry of Education, Culture and Research of the Republic of Moldova, National Rectors` Council, HEIs` academic and administrative staff, students | 1. Rector 2. Vice-rector for international affairs 3. Head of International Relations Offices/Departments 4. Ministry's Representatives 5. National Rectors` members | 1. space maintenance and servicing costs 2. protocol expenses 3. office supplies / consumables The expenses will be covered from institutional sources, sources accumulated from sponsors. | 1. Number of the experts meetings organised on regulatory development of Iohe in Moldova ; 2) Number of proposal to improve the regulatory framework on IoHE, 3) New bylaws regulations on Iohe at system level; 4) annual data collection and improvement of online benchmarking tool.
D3.1 & D3.3 | University Guideline for increasing the quality and scope of academic mobility and recognition of mobility | 1. To imprive the academic procedures on organisation and realisation of academic mobilities of students and staff in order to ensure fair and transparent conditions for all; 2. To promote automatic mutual recognition of qualifications and learning periods abroad. | 1. To keep the academic community informed through institutional means of communication; 2. To stimulate the academic mobility by extending the list of internation partners. | Students, academic staff, administrative staff | 1. Rector 2. Vice-rector for international affairs 3. Head of International Relations Offices/Departments | 1. space maintenance and servicing costs 2. protocol expenses 3. office supplies / consumables The expenses will be covered from institutional sources, sources accumulated from sponsors. | 1) Increased efficient management of ICM, bilaterial mobility schemes; 2) Number of feedback (satisfaction survey) from students on management of student mobility programmes; 3) Number of satisfaction surveys (feedbacks ) from academic and administrative staff on management of staff mobility programme; 4) Number of satisfaction surveys (fedbacks) from researchers on management of research mobility programmes.
D3.2 | Internationalisation strategies and Action Plans | 1. To enhance the international profile of the Higher Education Institution on international arena by implementation of internationalisation tools; 2. To internationalise curriculum through elaboration and modernisation of joint-double degreese study programs, enlarging the variaty of courses taught in international language, especially English; 3. To strengthen research and knowledge production and promote through international chanels; 4. To diversify academic community and atract international students through promoting the diversity culture within the HEI. | 1. To support digitalisation of curriculum (e-leanring aspects; 2. to focus on Internationalisation ayt home at institutional level; 3. to encourange the virtual exchange mobility programms, 4. To support multicultural university environment and promote inter-cultural dialogue; To increase the world university rankings of the HEIs in Moldova. | HEIs` students, academic and administrative staff, researchers. | 1. Rector 2. Vice-rector for international affairs 3. Head of International Relations Offices/Departments | 1. space maintenance and servicing costs 2. protocol expenses 3. office supplies / consumables The expenses will be covered from institutional sources, sources accumulated from sponsors. | 1. Number of joint or double degree study programmes, 2. number of courses delivered in English language, 3) number of invited international teachers and researchers, 4) number of ougoing and incoming students, staff and researchers, 5) number of international students; 6) number of Multicultural events at universities, 7) position in World University rankings (ex. U-Multirank, Eduniversal, THE university ranking, Webometrics), 8) Number of Strategic Agreements on Cooperation.
D4.2-D4.4 | 1. Institutional rules & recommendations for recruitment elaborated; 2. Action Plan for participation in the European Research Area; 3. Set of recommendations for university research project management and talent development. | 1. To promote the international academic staff recruitment in order to diversify the HEIs' staff profile, improve the educational programs, offer creative teaching ideas, broadened students’ horizons through talking about different contextual experiences and backgrounds, support students through cultural transitions; 2. To foster the integration in ERA at institutional level by supporting the Open Science initiatives and tools, by obtaining the EURAXESS label on Excelnec in research; 3. To promote open labour market for researchers by facilitating mobility, supporting training and ensuring attractive careers. | 1. To attract international academic staff and increase the number of foreign leacturers though participation of HEIs at academic fairs and international collaborations; 2. To cooperate with National Academy of Science and other national stakeholders through mutual organisation of large scale events organised for promotion of reserch potential on national and international level; 3. To support initiatives for Open Science impementation in Moldova; 4) to support initiative to obtaine the EURAXESS label on Excellence in research by HEIs in Moldova; 5. To encourange the mobility of young reserchers by extending the international collaborations of higher education institution. | HEIs` academic staff and administrative staff, researchers, Scientific organisations, thnk-tank, founders | 1. Rector 2. Vice-rector for scientific activity; 3. Vice-rector on international affairs 4. Head of reaserch department/ research laboratorie; 5. Head/oficers of the International Relations Offices | 1. space maintenance and servicing costs 2. protocol expenses 3. office supplies / consumables The expenses will be covered from institutional sources, sources accumulated from sponsors. | 1. Number of international professors and researchers recruted; 2) Number of regulatory documents on Open Science tools adopted (ex. On Open access, institutional repositories, Open data, Open research evaluation, anti-plagiarism, etc) 3) Number of the HEIs with the EURAXESS label on Excellence in research obtained, 4) number of the international research projects.